**Update from the Office of Children’s Mental Health (OCMH) for the**

**September 9th, 2015 CST Statewide Project Directors’ Meeting**

| **Placement on Public Health Pyramid** | **Action Item** | **Activity / Outcome(s)** | **Person(s)**  **Responsible** | **Time-**  **frame** | **Status** |
| --- | --- | --- | --- | --- | --- |
| Universal | **1. Brighter Futures**  Lead: DCF  (DHS) | Prevent and reduce violence, AODA, CAN, and adolescent pregnancies | Wendy Henderson | Ongoing | Portage, Kenosha, Dane, Washington, Barron, and Outagamie. Red Cliff Tribe. Services began in March of 2015. |
|  |
| Universal | **2. Safe Schools Healthy Students**  Lead: DPI  (DCF/DHS/DOC/  OCMH) | Promote early childhood social and emotional learning, positive behavioral health, link families, schools and communities and create safe and violent-free schools | Christie Gause-Bemis (cross-department position) | 2013 - 2017 | Menominee Tribe, Racine, and Beloit implementing trauma sensitive schools, community engagement, SBIRT, and school mental health clinics.  Workgroups for the state leadership team are developing products for use statewide on school mental health, school climate, and family engagement. |
| Beth Herman-Ukasick |
| Monica  Wightman |
| Universal | **3. Project AWARE**  Lead: DPI  (DCF/DHS/DOC/  OCMH) | Enhance coordination, school safety and integration of mental and behavioral health services | Beth Herman-Ukasick | 2014 - 2019 | Adams – Friendship, Ashland and Milwaukee  This project is being run in tandem with the Safe Schools-Healthy Students project.  Community teams drafted 4 year plans. |
| Monica Wightman |
| Christie Gause-Bemis |
| Universal | **4. School Climate Transformation/**  **Wisconsin School Mental Health**  Lead: DPI  (OCMH/DCF) | Support PBIS, develop a school-based mental health training, enhance supports for social and emotional development | Doug White | 2014 – 2019 | 50 school-community teams selected. Professional development planned to begin 8/15, to include trauma sensitive schools. WI PBIS Network added 2 staff. |
| Kathryn Bush |
| Universal | **5. SAAD**  Lead: OCMH  (DPI/DOC/DCF/DHS) | Identify state agency activities related to reducing disparities | Kate McCoy | Ongoing | Held two meetings. *Understanding Historical Trauma* presentation scheduled for August. |
| Courtney Jenkins |
| Universal | **6. ECAC**  Lead: DCF/DPI  (DHS/OCMH) | Promote cross-system coordination of efforts | Jennie Mauer | Ongoing | Developing strategic plan |
| Bridget Cullen |
| Universal | **7. RTTT-ELC**  Lead: DCF  (DHS/DPI) | Reinforce YoungStar,  strengthen family engagement, create early childhood longitudinal data system | Mandy Besner | 2013-2016 | Mid-State Tech College, Milw Area Tech College, UW-Platteville, Moraine Park Tech College, North Central Tech College, Northeast WI Tech College, Waukesha Co Tech College and Western Tech College provide credits to 2 & 3 Star programs to complete credentials |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Universal | **8. New! Leading Together**  Lead: DHS  (DPI/OCMH) | Support family leadership within state and county level policy, program, and quality improvement activities initiatives | Barb Katz | Ongoing | Plans to bring together state agencies, family leaders and family supporting organizations |
| Sue Latton |
| Joann Stephens |
| Universal | **9. Family Foundations Home Visiting**  Lead: DCF  (DHS/DPI/OCMH) | Provide support to families from pregnancy to 8 yrs old with focus on parenting, school readiness, health and preventing child abuse and neglect | Leslie McAllister | Ongoing | Fourteen programs |
| Linda Benton |
| Universal | **10. New! Connections Count**  Lead: DCF  (FF Policy Advisory Council) | Focus on families with children 0-5; a trusted community member connects families to resources | Judie Hermann | 2016-2017 | First year planning second year serve 1,000 families |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Secondary | **11. Fostering Futures**,  Lead: First Lady Walker  (DCF/DHS/DOC/DPI/OCMH) | Implement TIC across Wisconsin with a focus on ages 0-5 | Fredi Bove | Ongoing | Phase 1: complete  Phase 2: planning stage  Summits held May 20 & 21  Website launched: <http://www.fosteringfutureswisconsin.org/> |
| Elizabeth Hudson |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Secondary | **12. Child Psychiatry Consultation Program**  Lead: DHS  (DCF/OCMH) | Provide consultation and education to primary care clinicians on children’s mental health needs | Leah Ludlum | Began January 2015 | Medical College and Children’s Hospital Milwaukee: 23 clinics representing approx. 132 providers. Northern: 21 clinics presenting approx. 84 providers. 111 encounters with  reasons for contact being: Medication Question (81), Diagnostic (19), Second Opinion (17). |
| Secondary | **13. SBIRT**  Lead: DPI  (DHS) |  | Scott Caldwell |  |  |
| Secondary | **14. InSPIRE**  Lead: DPI  (DHS/DCF/UW Extension/Technical College) | Assist school-age parents complete their high school education; connect them to higher education; teach positive parenting and child development | Emily Holder | Funding through July 2017 | 13 school districts: Adams-Friendship, Bayfield, Beloit, CESA 3, Fond du Lac, Green Bay, Janesville, Madison, Menominee, Milwaukee, Racine, Walworth Consortium, West Allis – West Milwaukee |
| Secondary | **15. Early Childhood Comprehensive Systems Grant**  Lead: DHS  (DCF/WIAIMH/  Fostering Futures) | Train therapists in Child Parent Psychotherapy;  Train parents, caregivers and case workers in effects of trauma on children;  TIC introduction in the community | Leah Ludlum | Funding through July 2016 | Waupaca, Rock, Kenosha |
| Amy D’Addario |
| Tertiary | **16. Care 4 Kids**  Leads: DHS/DCF | Coordinated care | Fredi Bove | Began January 2014 | Enrollment started with new CPS entrants, existing children in the system started enrollment on July 1, 2014. **2,762 children enrolled**. |
| Rachel Currens-Henry |
| Deb Rathermel |
| Tertiary | **17. Children’s Behavioral Health Initiative**  Lead: DHS  (DCF, OCMH, DPI) | Analysis of prescriber practices; Identify possible Medicaid interventions; Increase education and awareness of evidence-based non-pharmaceutical interventions | Faith Russell | Ongoing | Division of Public Health developed a data base on the use of psychotropics; Data review underway to identify therapies children receive in addition to medications DHCAA reviewing strategies that could be implemented in the Medicaid program; DPI data now available to be linked; Further exploration of trends in diagnosis |
| Tertiary | **18. Systems of Care Transformation**  Lead: DHS  (DCF/DPI/DOC/  OCMH) | Expand the comprehensive, individualized system of care for children with complex behavioral health needs | Joanette Robertson | Ongoing | 35 tribes and counties are implementing. Burnett County and possibly Taylor County will implement in 2015.Bayfield, Rusk, Outagamie and Winnebago have not applied. |
| Karen Bittner |
| Rebecca Wigg-Ninham |
| Tertiary | **19. PATHS Grant**  Lead: DCF  (DPI/DHS/DOC/  OCMH) | **P**ermanent Connections, **A**cademics,  **T**raining and Employment, **H**ousing,  **S**ocial and Emotional Well-being | Wendy Henderson | Two year planning grant with possible expansion | PATHS grant pilot sites to reduce homelessness among vulnerable youth: Dane County, Rock County, and a four-county consortium composed of Sheboygan, Door, Kewaunee and Manitowoc Counties. Implementation began in August of 2014. |
| Christina Lenske |
| Joyce Allen |
| Fredi Bove |
| Tertiary | **20. Post-Reunification Support Program (PS)**  Lead: DCF  (DHS) | Use IV-E funds more flexibly and reduce re-entry to foster care by providing case management, | Vaughn Brandt | Thru Sept 2018 | To date the PS Program had served 360 children. 154 of those children were new enrollees in 2015, 212 are being actively served. 31 counties have children enrolled this year. 75 children have successfully reunified for the 12 month period with another 33 on track to complete in the next 60 days. The IV-E Waiver in the “balance of state” |
| Tertiary | **21. Now is the Time Healthy Transitions Grant**  16 – 25 years old.  Lead: DHS  (DCF/DPI/OCMH) | Increase awareness of early signs of serious mental health concerns; Identify action strategies to use when a serious mental health concern is detected; Enhance peer and family supports; Develop effective services and interventions for youth, young adults and their families as they transition to adulthood | Sally Raschick | 2014 - 2019 | Two pilot counties: Outagamie and Jefferson  State level includes: Project director, Youth coordinator, Social media specialist  County level includes: Project director, Youth coordinator, Parent peer specialist  Help needed to facilitate school involvement |
| Tertiary | **22. New! Collaborative for Change:**  **Mental Health Training Initiative for State and Local Juvenile Justice Systems**  Lead: DOC  (DHS/DCF/OCMH) | 20-40 trainers participate in a train the trainer process | Joyce Allen | June 2015- Jun 2016 | First train-the-trainer will be held in March of 2016; trainers have been identified. The co-trainer training teams include one juvenile justice and one mental health professional |
| Paul Westerhaus |
| Tertiary | **23. New! Policy Academy on Justice Involved Youth with Behavior Health Disorders**  Lead: DHS  (DOC/DCF/DPI/  OCMH) | Create a school-based diversion from juvenile justice on the local level; address policies on the statewide level; participate in action planning to change policy on the national level;  WI was dually chosen to receive assistance in addressing disproportionality | Joyce Allen | 2015 - 2016 | Core team is established (five state and three local members);  Building the home team (other stakeholders);  Draft plan for the school-based diversion in Rock County/Beloit school district |
| Tertiary | **24. New! Garrett Lee Smith Grant**  Lead: Mental Health America  (DHS/DCF/DPI/DOC/OCMH) | Reduce suicides in WI | Shel Gross |  | Submitted |
| Tertiary | **25. Emergency Detention Crisis Stabilization Workgroup**  Lead: OCMH  (DCF, DHS) | Examine ED rates and the availability and use of a service continuum of care; Make recommendations leading to a reduction of EDs | Kate McCoy | On-going | Identify root causes of increase in EDs and make subsequent recommendations. Collecting data and insights from counties |
| Tertiary | **26. New! Wisconsin System of Care Implementation Academy**  Lead: DHS  (OCMH, DCF) | On-site technical assistance from Georgetown University, National Technical Assistance Center for Children’s Mental Health.  The technical assistance is to further develop the Children’s Mental Health System of Care within the State. | Theresa Steinmetz |  | Team attended one day academy July 30. |
| Tertiary | **27. Collective Impact**  Lead: OCMH  (DPI/DHS/DCF/DOC) | Increase access to effective services, Promote TIC in child serving agencies; Increase child, family and community resiliency | Kate McCoy | Ongoing | Three workgroups:   * Access * Trauma-Informed Care; * Resiliency   Next topic: shared measures |
| Joann Stephens |
| Kim Eithun |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Projects to be aware of but are not based in state agency collaboration** | | | | | |
| Universal | **School Safety Research**  DPI | Ongoing  Study the impact of PBIS plus bullying prevention in middle schools | John Bowser | 2015 - 2017 | 31 middle schools recruited. Evaluation planned. |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Secondary | **DCF Trauma Project**  DCF | Train mental health clinicians in TF-CBT; Train parents, caregivers and case workers in effects of trauma on children; TIC training in the community | Bonnie MacRitchie | Approx three to four sites per year | 2015 sites: Rock/Walworth/Jefferson  Existing sites: Barron/Burnett/St. Croix  Tribe; Kenosha; Outagamie/Oneida Tribe; La Crosse; Grant; Crawford; Green; Lafayette; Iowa; Polk; Jackson |
|  |
| Tertiary | **Expansion of In-home Counseling for Children**  DHS | Provide children’s in-home counseling |  | Funding provided in 2013-2015 budget | DHCAA issued a provider bulletin to certified outpatient clinics in Oct/Nov; Current data is from 2013 when expansion was introduced halfway through the year. 2014 should be available soon. |
| Tertiary | **Comprehensive Community Services Expansion**  DHS | Provide programming to reduce reliance on high-end services such as emergency rooms and in-patient stays | Cheryl Lofton | Ongoing | 39 counties are certified as of Oct 2014. 11 counties do not intend to provide CCS as of July 2015. |
| Tertiary | **New! WI Juvenile Justice Network** | Provide best practice for juvenile justice | Jim Moeser | Ongoing | Launching a website with best practices |
| Joann Stephens |
| Tertiary | **Tele-psychiatry Consultation** **Mendota Mental Health Institute**  DHS | Provide tele-psychiatric services to clients | Dr. Rowley | Ongoing | Established rates of $225/hr  Adams and Winnebago counties have signed contracts. |
| Wendy LaBine |